## Cover Sheet
Institute for Veterans and Military Families Research Portal
Team Members:
Rachel James Pulkit Jain Kirti Jaisinghani Ishani Jariwala Gauri Komawar Monika Pawar Mohit Rao
Summary of Updates as of 12/02:
For our last submission we submitted planning and sprint artifacts. This submission includes corrections as per review comments and Monitoring/controlling – sprinting artifacts.

## Table of Contents
Table of Contents
Page Number
Responsibility Assignment Matrix |  |  | 1
Product Vision |  |  | 2
Project Charter |  |  | 3
Business Case |  |  | 4
Envisioning Artifacts
| Use Case Diagram |  | 5
| Product Backlog |  | 6
| User Stories |  | 7
| Product Roadmap |  | 8
Planning Artifacts
| Release Constraints |  | 9
| Risk Analyses |  | 10
| Groomed Product Backlog |  | 11
| Story Maps |  | 12
Sprint Planning
| Sprint Backlog |  | 13
| Cost Estimates |  | 14
Monitoring/controlling – sprinting
| Burn up Chart |  | 13
| Earned Value Management (EVM) metrics |  | 15
| Cumulative flow diagrams (CFDs) |  | 16
| Velocity tracking charts |  | 17
| Parking lot diagrams |  | 18
Note on B4: Travis C. LePage: Looks good

## RAM
Responsibility Assignment Matrix
| Week 1&2 (Sep 30 - Oct 13) |  |  | Week 3 & 4 (Oct 14 - Oct 27) |  |  | Week 4 & 5 (Oct 28 - Nov 10) |  |  | Week 6 & 7 (Nov 11 - Dec 2)
Roles Names | PO | SM | DT | PO | SM | DT | PO | SM | DT | PO | SM | DT
Ishani Jariwala | X |  |  |  | X |  |  |  | X |  |  | X
Monika Pawar |  | X |  |  |  | X | X |  |  |  | X
Pulkit Jain |  | X |  |  |  | X | X |  |  |  |  | X
Kirti Jaisinghani | X |  |  |  |  | X |  | X |  | X
Rachel James |  |  | X | X |  |  |  |  | X |  | X
Mohit Rao |  |  | X | X |  |  |  | X |  |  |  | X
Gauri Komawar |  |  | X |  | X |  |  |  | X | X

## Product Vision
Product Vision
Elevator Statement:
FOR: | IVMF
WHO: | Collaboratives and Researchers
THE: | CDART
IS A: | Web Portal
THAT: | Enabling organisations and collaboratives to analyze their network hierarchies
UNLIKE: | None
WE: | Innovative Tool
Product Box
Note on A41: Travis C. LePage: Graphic was missing from submission. I added it from the last one

## Project Charter
Project Charter

## Business Case
Business Case

## Use Case Diagram
Use Case Diagram

## Product Backlog
Risk-adjusted Product Backlog for CDART
Red Indicates Negative Risks
Green Indicates Oppurtunities
| ID | Story | Priority
| 17 | As an administrator, I want to re-structure data from the relational database so that I can query the data quickly | 1
| 18 | As a organization/collaborative user, I want to search collaboratives and organizations based on state so I can get list of organizations in that state to approach | 2
| 19 | As an administrator, I want to search collaboratives and organizations based on state so I can get list of organizations in that state | 3
| 24 | As a researcher, I want to search collaboratives and organizations based on location so I can get list of organizations in that state | 4
| 25 | As a user, I want to access the tool results quickly so that the tool performance is fast | 5
| 26 | As a organization/collaborative user, I want to search collaboratives and organizations based on county so I can get list of organizations in that locality to approach | 6
| 27 | As an administrator, I want to search collaboratives and organizations based on county so I can get list of organizations in that locality for IVMF programs | 7
| 14 | As a researcher, I want to search collaboratives and organizations based on county so I can get list of organizations in that locality | 8
| 16 | As a user, I want the collaborative/organization information to be upto date, so that I can access the latest information about the organizations/collaboratives | 9
| 15 | As a organization/collaborative user, I want to search collaboratives and organizations based on zip so I can get list of organizations in that locality to approach | 10
| 11 | As an administrator, I want to search collaboratives and organizations based on zip so I can get list of organizations in that locality for IVMF programs | 11
| 12 | As a researcher, I want to search collaboratives and organizations based on zip so I can get list of organizations in that locality | 12
| 13 | As an administrator, I want to build a unique system that displays the complete description of all organizations/collbortative in the nation, so that any researcher/user can access the data with ease | 13
| 9 | As a organization/collaborative user, I want to search collaboratives and organizations based on city so I can get list of organizations in that locality to approach | 14
| 8 | As an administrator, I want to search collaboratives and organizations based on city so I can get list of organizations in that locality for IVMF programs | 15
| 10 | As a researcher, I want to search collaboratives and organizations based on city so I can get list of organizations in that locality | 16
| 2 | As a user, I want the system to have all browser compactibility, so that I can easily access the system with any browser | 17
| 1 | As a organization/collaborative user, I want to view the collaborative details so I can know about other collaboratives work | 18
| 3 | As a researchers, I want to view the collaborative details so I can know about collaboratives work | 19
| 20 | As a researcher, I want to view the data visualization reports so I can see the network relations of organizations | 20
| 21 | As a organization/collaborative user, I want to view the data visualization reports so I can see the network relations of other organizations | 21
| 29 | As an administrator, I want to view the data visualization reports so I can see the network relations of different organizations | 22
| 23 | As an administrator, I want to view the collaborative details so I can know about collaboratives work | 23
| 7 | As an administrator, I want to view the data visualization reports so I can see the network relations of organizations | 24
| 4 | As an administrator, I want to search collaboratives and organizations based on type of collaborative so I can get list of organizations within that category | 25
| 6 | As a organization/collaborative user, I want to search collaboratives and organizations based on type of collaborative so I can get list of organizations within that category | 26
| 5 | As a organization/collaborative user, I want to search collaboratives and organizations based on service areas so I can get list of organizations providing a particular service | 27
| 28 | As an administrator, I want to search collaboratives based on service areas so I can get list of organizations providing a particular service | 28
| 30 | As a organization/collaborative user, I want to search collaboratives and organizations based on outreach so I can get list of organizations which are nationwide or statewide | 29
| 22 | As an administrator, I want to search collaboratives based on outreach so I can get list of organizations which are nationwide or statewide | 30
| 41 | As a organization/collaborative user, I want to search collaboratives and organizations based on age of the organization so I can get list of organizations which are serving since that period | 31
| 42 | As an administrator, I want to search collaboratives based on age of the organization so I can get list of organizations which are serving since that period | 32
| 43 | As a organization/collaborative user, I want to search collaboratives and organizations based on network function category so I can get list of organizations which belong to similar category | 33
| 40 | As an administrator, I want to search collaboratives based on network function category so I can get list of organizations which belong to similar category | 34
| 32 | As a organization/collaborative user, I want to search collaboratives and organizations based on degree of formality so I can approach organization with that degree of formality | 35
| 33 | As an administrator, I want to search collaboratives based on degree of formality so I can approach organization with that degree of formality | 36
| 31 | As a organization/collaborative user, I want to search collaboratives and organizations based on government participation so I can decide whether to collaborative with them or not | 37
| 38 | As an administrator, I want to search collaboratives based on government participation so we can consider them for government related services | 38
| 39 | As an administrator, I want the ability to add new organization details so we can add new entities to the network | 39
| 34 | As a organization/collaborative user, I want to enter my organization/collaborative details so I can see my details added on the portal | 40
| 35 | As a organization/collaborative user, I want the ability to edit my details so I can get my details up to date on the portal | 41
| 36 | As an administrator, I want the ability to edit organization details so we can get organization details up to date on the portal | 42
| 37 | As an administrator, I want to delete organization details so we can get organization details off the portal | 43
| 44 | As a organization/collaborative user, I want to delete my details so I can get my organization details off the portal | 44
| 45 | As a organization/collaborative user, I want to export data visualization reports so I can refer the details later | 45
| 46 | As an administrator, I want to export data visualization reports so I can use them for grant applications | 46
| 47 | As a researcher, I want to export data visualization reports so I can refer the details later for research | 47
| 48 | As an administrator, I want to approve organization/collaborative details added so that errorneous details are not updated on the portal | 48
| 49 | As a developer, I want to explore different tools so that I can help make better dashboards | 49
| 50 | As a developer, I want to explore the exisitng relational database so that I can know the data well | 50
| 51 | As a developer, I want to clean the data so that I can import correct data for the dashboard | 51
| 52 | As a user, I want to have auto-fill options so that I can have a good search filter user friendly experience | 52

## User Stories
User Stories
Epic | Build CDART
Theme | Search by Location | Theme | View Collaborative Details | Theme | Search by Collaborative Details | Theme | Collaborative Details Forms
Stories | As a organization/collaborative user, I want to search collaboratives and organizations based on state so I can get list of organizations in that state to approach | Stories | As a organization/collaborative user, I want to view the collaborative details so I can know about other collaboratives work | Stories | As an administrator, I want to search collaboratives and organizations based on type of collaborative so I can get list of organizations within that category | Stories | As an administrator, I want the ability to add new organization details so we can add new entities to the network
Stories | As an administrator, I want to search collaboratives and organizations based on state so I can get list of organizations in that state | Stories | As a researchers, I want to view the collaborative details so I can know about collaboratives work | Stories | As a organization/collaborative user, I want to search collaboratives and organizations based on type of collaborative so I can get list of organizations within that category | Stories | As a organization/collaborative user, I want to enter my organization/collaborative details so I can see my details added on the portal
Stories | As a researcher, I want to search collaboratives and organizations based on location so I can get list of organizations in that state | Stories | As a researcher, I want to view the data visualization reports so I can see the network relations of organizations | Stories | As a organization/collaborative user, I want to search collaboratives and organizations based on service areas so I can get list of organizations providing a particular service | Stories | As a organization/collaborative user, I want the ability to edit my details so I can get my details up to date on the portal
Stories | As a organization/collaborative user, I want to search collaboratives and organizations based on county so I can get list of organizations in that locality to approach | Stories | As a organization/collaborative user, I want to view the data visualization reports so I can see the network relations of other organizations | Stories | As an administrator, I want to search collaboratives based on service areas so I can get list of organizations providing a particular service | Stories | As an administrator, I want the ability to edit organization details so we can get organization details up to date on the portal
Stories | As an administrator, I want to search collaboratives and organizations based on county so I can get list of organizations in that locality for IVMF programs | Stories | As an administrator, I want to view the data visualization reports so I can see the network relations of different organizations | Stories | As a organization/collaborative user, I want to search collaboratives and organizations based on outreach so I can get list of organizations which are nationwide or statewide | Stories | As an administrator, I want to delete organization details so we can get organization details off the portal
Stories | As a researcher, I want to search collaboratives and organizations based on county so I can get list of organizations in that locality | Stories | As an administrator, I want to view the collaborative details so I can know about collaboratives work | Stories | As an administrator, I want to search collaboratives based on outreach so I can get list of organizations which are nationwide or statewide | Stories | As a organization/collaborative user, I want to delete my details so I can get my organization details off the portal
Stories | As a organization/collaborative user, I want to search collaboratives and organizations based on zip so I can get list of organizations in that locality to approach | Stories | As an administrator, I want to view the data visualization reports so I can see the network relations of organizations | Stories | As a organization/collaborative user, I want to search collaboratives and organizations based on age of the organization so I can get list of organizations which are serving since that period | Stories | As an administrator, I want to approve organization/collaborative details added so that errorneous details are not updated on the portal
Stories | As an administrator, I want to search collaboratives and organizations based on zip so I can get list of organizations in that locality for IVMF programs | Stories | As a organization/collaborative user, I want to export data visualization reports so I can refer the details later | Stories | As an administrator, I want to search collaboratives based on age of the organization so I can get list of organizations which are serving since that period
Stories | As a researcher, I want to search collaboratives and organizations based on zip so I can get list of organizations in that locality | Stories | As an administrator, I want to export data visualization reports so I can use them for grant applications | Stories | As a organization/collaborative user, I want to search collaboratives and organizations based on network function category so I can get list of organizations which belong to similar category
Stories | As a organization/collaborative user, I want to search collaboratives and organizations based on city so I can get list of organizations in that locality to approach | Stories | As a researcher, I want to export data visualization reports so I can refer the details later for research | Stories | As an administrator, I want to search collaboratives based on network function category so I can get list of organizations which belong to similar category
Stories | As an administrator, I want to search collaboratives and organizations based on city so I can get list of organizations in that locality for IVMF programs |  |  | Stories | As a organization/collaborative user, I want to search collaboratives and organizations based on degree of formality so I can approach organization with that degree of formality
Stories | As a researcher, I want to search collaboratives and organizations based on city so I can get list of organizations in that locality |  |  | Stories | As an administrator, I want to search collaboratives based on degree of formality so I can approach organization with that degree of formality
Stories | As a developer, I want to explore different tools so that I can help make better dashboards |  |  | Stories | As a organization/collaborative user, I want to search collaboratives and organizations based on government participation so I can decide whether to collaborative with them or not
Stories | As a developer, I want to explore the exisitng relational database so that I can know the data well |  |  | Stories | As an administrator, I want to search collaboratives based on government participation so we can consider them for government related services
Stories | As a developer, I want to clean the data so that I can import correct data for the dashboard |  |  | Stories | As a user, I want to have auto-fill options so that I can have a good search filter user friendly experience

## Product Roadmap
Product Roadmap
First Release
Backbone | Search by Location |  | View Collaborative Details | Search by collaborative Details |  | Collaborative Details Form
Walking Skeleton | As a developer, I want to explore different tools so that I can help make better dashboards | As a developer, I want to explore the existing relational database so that I can know the data well | As an organization/ collaborative user/Researchers/Administrator, I want to view the collaborative details so I can know about other collaborative work | As an organization/ collaborative user/Researchers/Administrator, I want to search collaborative and organizations based on type of collaborative so I can get list of organizations within that category | As an organization/ collaborative user/Researchers/Administrator, I want to have auto-fill options so that I can have a good search filter user friendly experience
| As a developer, I want to clean the data so that I can import correct data for the dashboard | As an organization/ collaborative user/Researchers/Administrator, I want to search collaborative and organizations based on state so I can get list of organizations in that state to approach
| As an organization/ collaborative user/Researchers/Administrator, I want to search collaborative and organizations based on zip so I can get list of organizations in that locality to approach | As an organization/ collaborative user/Researchers/Administrator, I want to search collaborative and organizations based on county so I can get list of organizations in that locality to approach
Second Release
| As an organization/ collaborative user/Researchers/Administrator, I want to search collaborative and organizations based on city so I can get list of organizations in that locality to approach |  | As an organization/ collaborative user/Researchers/Administrator, I want to view the data visualization reports so I can see the network relations of organizations | As an organization/ collaborative user/Researchers/Administrator, I want to search collaborative and organizations based on service areas so I can get list of organizations providing a particular service |  | As an administrator/ organization/ collaborative, I want the ability to add new organization details so we can add new entities to the network
|  |  |  | As an organization/ collaborative user/Researchers/Administrator, I want to search collaborative and organizations based on network function category so I can get list of organizations which belong to similar category |  | As an administrator/ organization/ collaborative, I want the ability to edit organization details so we can get organization details up to date on the portal
Third Release
|  |  | As an organization/ collaborative user/Researchers/Administrator, I want to export data visualization reports so I can use them for grant applications | As an organization/ collaborative user/Researchers/Administrator, I want to search collaborative and organizations based on outreach so I can get list of organizations which are nationwide or statewide | As an organization/ collaborative user/Researchers/Administrator, I want to search collaborative and organizations based on degree of formality so I can approach organization with that degree of formality | As an administrator, I want to delete organization details so we can get organization details off the portal
|  |  |  | As an organization/ collaborative user/Researchers/Administrator, I want to search collaborative and organizations based on age of the organization so I can get list of organizations which are serving since that period | As an organization/ collaborative user/Researchers/Administrator, I want to search collaborative and organizations based on government participation so I can decide whether to collaborative with them or not | As an administrator, I want to approve organization/collaborative details added so that erroneous details are not updated on the portal
Note on T3: Travis C. LePage: It's good to see that you used an online tool, but what is the timescale? What is the definition of "near term," "Future?" I would prefer to see the story maps and then product roadmap in this format, which could be sticky notes on the whiteboard and a picture of it. Use online tools to memorialize what the team developed in-person on the white boards. Where is the "backbone" and "walking skeleton" See example below.

## Release Constraints
Release Constraints
Theme | Scope | Date | Budget
Remapping Data | Fixed | Flexible | Flexible
Search by Location | Flexible | Fixed | Fixed
View Collaborative details | Fixed | Flexible | Flexible
Search by Collaborative details | Flexible | Fixed | Flexible
Collaborative Details forms | Fixed | Flexible | Fixed

## Risk Analyses
Risk Analyses
ID | Description | Probability % | Impact $ | EMV $
R5 | Re-structuring the relational database | 60% | 15000 | 9000
R2 | Web Site performance and load handling | 15% | 15000 | 2250
R3 | Maintaining latest information about the organozation/collaborative | 40% | 15000 | 6000
R1 | Building a unique system which helps researcher/user to access nation's organization data | 10% | 10000 | 1000
R4 | Browser Compatibility | 40% | 150 | 60
Themes | Stories(Risk Response) | User Acceptance Criteria | Estimation (Story points) | Task
Search by Location | Sprint 01
| [Risk Response : R5] As an administrator, I want to re-structure data from the relational database so that I can query the data quickly | Verify that the data is well linked | 11 | Task1: Analyse Relational Database Task2: Identify required entities
| [Risk Response : R5] As a developer, I want to clean the data so that I can import correct data for the dashboard | Verify that all data is imported without any data loss | 9 | Task1: Create high level dimensional model Task2: Load data in dimensional model Task3: Create multi dimensional cube database
| As a organization/collaborative user, I want to search collaboratives and organizations based on state so I can get list of organizations in that state to approach | Verify that all states are visible on the map | 21 | Task1: Analyse data Task2: Data Cleaning Task3: import data Task4: Design menu bar Task5: Creating Map Task6: Create state filter Task7: Publish to website Task8: Test state data
| As an administrator, I want to search collaboratives and organizations based on state so I can get list of organizations in that state | Verify that a list of orgs is created statewise
| As a researcher, I want to search collaboratives and organizations based on location so I can get list of organizations in that state | Verify that Google maps framework is used
| [Risk Response : R2] As a user, I want to access the tool results quickly so that the tool performance is fast | Verify that result is returned in 3 seconds | 13 | Task1: Build queries Task2: Run performance tunning Task3: Configure maintainence cycle
Sprint 02
| As a organization/collaborative user, I want to search collaboratives and organizations based on county so I can get list of organizations in that locality to approach | Verify that fields are auto filled | 13 | Task1: Analyse data Task2: Data Cleaning Task3: import data Task4: Design menu bar Task5: Creating Map Task6: Create county filter Task7: Publish to website Task8: Test County data
| As an administrator, I want to search collaboratives and organizations based on county so I can get list of organizations in that locality for IVMF programs | Verify that fields are auto filled
| As a researcher, I want to search collaboratives and organizations based on county so I can get list of organizations in that locality | Verify that fields are auto filled
| As a organization/collaborative user, I want to search collaboratives and organizations based on zip so I can get list of organizations in that locality to approach | Verify that incorrect Zipcode entered by user is detected | 13 | Task1: Analyse data Task2: Data Cleaning Task3: import data Task4: Design menu bar Task5: Creating Map Task6: Create zipcode filter Task7: Publish to website Task8: Test zipcode data
| As an administrator, I want to search collaboratives and organizations based on zip so I can get list of organizations in that locality for IVMF programs | Verify that incorrect Zipcode entered by user is detected
| As a researcher, I want to search collaboratives and organizations based on zip so I can get list of organizations in that locality | Verify that incorrect Zipcode entered by user is detected
| As a organization/collaborative user, I want to search collaboratives and organizations based on city so I can get list of organizations in that locality to approach | Verify that fields are auto filled | 13 | Task1: Analyse data Task2: Data Cleaning Task3: import data Task4: Design menu bar Task5: Creating Map Task6: Create city filter Task7: Publish to website Task8: Test city data
| As an administrator, I want to search collaboratives and organizations based on city so I can get list of organizations in that locality for IVMF programs | Verify that fields are auto filled
| As a researcher, I want to search collaboratives and organizations based on city so I can get list of organizations in that locality | Verify that fields are auto filled
| [Risk Response : R1] As a developer, I want to explore different tools so that I can help make better dashboards | Verify that the dashboard is user friendly which proper segregation of all serach crietias | 13 | Task1: Procure the tool Task2: Install the tool Task3: Import data Task4: Create sample visualization

## Groomed product backlog
Themes | Stories(Risk Response) | User Acceptance Criteria | Estimation (Story points) | Task
Search by Location | Sprint 01
| [Risk Response : R5] As an administrator, I want to re-structure data from the relational database so that I can query the data quickly | Verify that the data is well linked | 11 | Task1: Analyse Relational Database Task2: Identify required entities
| [Risk Response : R5] As a developer, I want to clean the data so that I can import correct data for the dashboard | Verify that all data is imported without any data loss | 9 | Task1: Create high level dimensional model Task2: Load data in dimensional model Task3: Create multi dimensional cube database
| As a organization/collaborative user, I want to search collaboratives and organizations based on state so I can get list of organizations in that state to approach | Verify that all states are visible on the map | 21 | Task1: Analyse data Task2: Data Cleaning Task3: import data Task4: Design menu bar Task5: Creating Map Task6: Create state filter Task7: Publish to website Task8: Test state data
| As an administrator, I want to search collaboratives and organizations based on state so I can get list of organizations in that state | Verify that a list of orgs is created statewise
| As a researcher, I want to search collaboratives and organizations based on location so I can get list of organizations in that state | Verify that Google maps framework is used
| [Risk Response : R2] As a user, I want to access the tool results quickly so that the tool performance is fast | Verify that result is returned in 3 seconds | 13 | Task1: Build queries Task2: Run performance tunning Task3: Configure maintainence cycle
Sprint 02
| As a organization/collaborative user, I want to search collaboratives and organizations based on county so I can get list of organizations in that locality to approach | Verify that fields are auto filled | 13 | Task1: Analyse data Task2: Data Cleaning Task3: import data Task4: Design menu bar Task5: Creating Map Task6: Create county filter Task7: Publish to website Task8: Test County data
| As an administrator, I want to search collaboratives and organizations based on county so I can get list of organizations in that locality for IVMF programs | Verify that fields are auto filled
| As a researcher, I want to search collaboratives and organizations based on county so I can get list of organizations in that locality | Verify that fields are auto filled
| As a organization/collaborative user, I want to search collaboratives and organizations based on zip so I can get list of organizations in that locality to approach | Verify that incorrect Zipcode entered by user is detected | 13 | Task1: Analyse data Task2: Data Cleaning Task3: import data Task4: Design menu bar Task5: Creating Map Task6: Create zipcode filter Task7: Publish to website Task8: Test zipcode data
| As an administrator, I want to search collaboratives and organizations based on zip so I can get list of organizations in that locality for IVMF programs | Verify that incorrect Zipcode entered by user is detected
| As a researcher, I want to search collaboratives and organizations based on zip so I can get list of organizations in that locality | Verify that incorrect Zipcode entered by user is detected
| As a organization/collaborative user, I want to search collaboratives and organizations based on city so I can get list of organizations in that locality to approach | Verify that fields are auto filled | 13 | Task1: Analyse data Task2: Data Cleaning Task3: import data Task4: Design menu bar Task5: Creating Map Task6: Create city filter Task7: Publish to website Task8: Test city data
| As an administrator, I want to search collaboratives and organizations based on city so I can get list of organizations in that locality for IVMF programs | Verify that fields are auto filled
| As a researcher, I want to search collaboratives and organizations based on city so I can get list of organizations in that locality | Verify that fields are auto filled
| [Risk Response : R1] As a developer, I want to explore different tools so that I can help make better dashboards | Verify that the dashboard is user friendly which proper segregation of all serach crietias | 13 | Task1: Procure the tool Task2: Install the tool Task3: Import data Task4: Create sample visualization

## Story Map
Story Maps
MMF
Page - 12

## Sprint Backlog
Sprint Backlog
Sprint Goal | The Sprint 1 goal is to complete the development of the CDART supporting data systems (analyze relational database and create the multidimensional database) so that the existing data will be available for the customer to search by location.
Backlog Item | Story Points | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Sprint Review
User Story #1 [Risk Response : R5] : As an administrator, I want to re-structure data from the relational database so that I can query the data quickly | 11 | Monika and Rachael | Complete
Task1: Analyse Relational Database |  |  |  | 8 | 1 | 2 | 3 | 5 | 7
Task2: Identify required entities |  |  |  | 3 | 1 | 1 | 0 | 0 | 1
User Story #2 [Risk Response : R5] : As a developer, I want to clean the data so that I can import correct data for the dashboard | 9 | Gauri and Kirti | Opened
Task1: Create high level dimensional model |  |  |  | 4 | 1 | 0 | 2 | 0 | 3
Task2: Load data in dimensional model |  |  |  | 3 | 0 | 1 | 1 | 1 | 0
Task3: Create multi dimensional cube database |  |  |  | 2 | 0 | 1 | 0 | 1 | 0
User Story #3 : As a organization/collaborative user/researcher/administrator, I want to search collaboratives and organizations based on state so I can get list of organizations in that state to approach | 21 | Ishani and Pulkit | Opened
Task1: Analyse data |  |  |  | 5 | 1 | 2 | 0 | 3 | 4
Task2: Data Cleaning |  |  |  | 6 | 1 | 2 | 3 | 0 | 5
Task3: Import data |  |  |  | 4 | 0.5 | 1.5 | 2 | 3 | 3.5
Task4: Design menu bar |  |  |  | 2 | 0.5 | 0.5 | 0 | 1 | 1.5
Task5: Creating Map |  |  |  | 1 | 0 | 0 | 1 | 0 | 0
Task6: Create state filter |  |  |  | 1 | 0 | 1 | 0 | 0 | 0
Task7: Publish to website |  |  |  | 1 | 1 | 0 | 0 | 0 | 0
Task8: Test state data |  |  |  | 1 | 1 | 0 | 0 | 0 | 0
User Story #4 [Risk Response : R2] : As a user, I want to access the tool results quickly so that the tool performance is fast | 13 | Mohit
Task1: Build queries |  |  |  | 9 | 0 | 0 | 0 | 0 | 0
Task2: Run performance tunning |  |  |  | 2 | 0 | 0 | 0 | 0 | 0
Task3: Configure maintainence cycle |  |  |  | 2 | 0 | 0 | 0 | 0 | 0
Total |  |  |  | 0 | 8 | 12 | 12 | 14 | 25

## Cost Estimation
Cost Estimation
Sprint No. | User Story | Estimated time(Days) | Team Members | Average Availabilty | Effort(Person_days)
Sprint-1 | User Story-1: As an administrator, I want to re-structure data from the relational database so that I can query the data quickly | 11 | Monica & Rachel | 0.75 | 14.6667
| User Story-2:As a developer, I want to clean the data so that I can import correct data for the dashboard | 9 | Gauri & Kirti | 0.8 | 11.25
| User Story-3:As a organization/collaborative user, I want to search collaboratives and organizations based on state so I can get list of organizations in that state to approach | 21 | Ishani & Pulkit | 0.85 | 24.7059
User Story-4 :As an administrator, I want to search collaboratives and organizations based on state so I can get list of organizations in that state
User Story-5: As a researcher, I want to search collaboratives and organizations based on location so I can get list of organizations in that state
| User Story-6: As a user, I want to access the tool results quickly so that the tool performance is fast | 13 | Mohit | 0.75 | 14.6667
0.7875
| Team Member | Hourly Rate
| Rachel | 50
| Monica | 60
| Mohit | 60
| Gauri | 50
| Ishani | 65
| Kirti | 65
350
| Total Effort | Σ Effort(F) | person_days
65.2
| Total Cost | (Total Time*Resource Rate) + other costs
**Assuming an 8-hour workday
| Labor Cost per day | (350*6*8)
16800
| Total Labor Cost | 16800*10.68
179424
| Deployment cost | 7000
| Warranty Cost | 2000
| Total Sprint Cost | Total Labor Cost+ Deployment Cost + Warranty Cost)
179424+ 7000+2000
188424
| Total Sprint Cost($) = | 188424

## EVM
Earned Value Management Metrics | [5 empty] | Cumulative Earned Value (EV)
[6 empty] | WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3
[6 empty] | 1.1 | Restructure Data | 170 | 25% | 30% | 45%
[6 empty] | 1.2 | Data Cleansing | 280 | 25% | 30% | 45%
[6 empty] | 1.3 | Indetify required entities | 350 | 20% | 60% | 20%
[6 empty] | 1.4 | Create dimensional model | 100 | 45% | 10% | 45%
[6 empty] | 1.5 | Load data | 80 | 100%
[6 empty] | 1.6 | Create multilevel cube | 160 | 10% | 20% | 70%
[8 empty] | Cumulative EV | 323.5 | 387 | 429.5
Actual Cost (AC) of Work Performed
[6 empty] | WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3
[6 empty] | 1.1 | Restructure Data |  | 110 | 60
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS) | [5 empty] | 1.2 | Data Cleansing |  | 110 | 110 | 60
WBS | Task Name | TBC | 1 | 2 | 3 | 1.3 | Indetify required entities |  | 80 | 180 | 90
1.1 | Restructure Data | 170 | 80 | 100 |  | 1.4 | Create dimensional model |  | 80 | 75 | 150
1.2 | Data Cleansing | 280 | 90 | 60 | 80 | 1.5 | Load data |  | 60
1.3 | Indetify required entities | 350 | 100 | 80 | 80 | 1.6 | Create multilevel cube |  | 80 | 80 | 80
1.4 | Create dimensional model | 100 | 60 | 80 | 100
1.5 | Load data | 80 | 50 |  |  | Insert new rows above this one
1.6 | Create multilevel cube | 160 | 80 | 80 |  |  |  | Total Actual Cost | 520 | 505 | 380
[8 empty] | Cumulative Actual Cost (AC) | 520 | 1025 | 1405
Insert new rows above this one
| Total Budgeted Cost | 1140 | 460 | 400 | 260
|  | Cumulative Planned Value (PV) | 460 | 860 | 1120
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 520 | 1025 | 1405
|  | Cumulative Earned Value (EV) | 323.5 | 387 | 429.5
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | -196.5 | -638 | -975.5
|  | Schedule Variance (SV = EV - PV) | -136.5 | -473 | -690.5
|  | Cost Performance Index (CPI = EV/AC) | 0.62212 | 0.37756 | 0.30569
|  | Schedule Performance Index (SPI = EV/PV) | 0.70326 | 0.45 | 0.38348
|  | Estimated Cost at Completion (EAC) | 1832.4575 | 3019.3798 | 3729.22
Note on A19: Work Breakdown Structure (WBS)
Note on C19: Total Budgeted Cost (TBC)

## CFD
Cumulative flow diagrams (CFDs)
Date | Backlog/New Items | Requested/Committed Work | In Progress/Doing | Done/Delivered
2016-09-30 | 2
2016-10-01 | 3 | 2
2016-10-02 | 3 | 2 | 1
2016-10-03 | 4 | 3 | 2 | 1
2016-10-04 | 5 | 3 | 2 | 2
2016-10-05 | 6 | 4 | 2 | 2
2016-10-06 | 9 | 5 | 4 | 2
2016-10-07 | 9 | 5 | 5 | 4
2016-10-08 | 12 | 7 | 5 | 5
2016-10-09 | 12 | 8 | 7 | 5
2016-10-10 | 13 | 10 | 7 | 6
2016-10-11 | 14 | 11 | 9 | 8
2016-10-12 | 15 | 14 | 11 | 8
2016-10-13 | 15 | 15 | 11 | 10

## Velocity Tracking Chart
Velocity Tracking Chart
| Sprint | Sprint Velocity
| 1 | 30
| 2 | 35
| 3 | 33
| 4 | 30
| 5 | 30
| Average Velocity | 31.6

## Parking Lot Diagram
Parking Lot Diagram
2016-12-09 | Todays date
Feature Group | Feature | Due Date | Col. Status | Work Status | % Complete | % Rem. | Graphic
Search by Location |  | 2016-12-29 | Blue |  | 30% | 70%
| Filter by State |  |  | 60% |  |  | Search by Location
| Filter by County |  |  | 20% |  |  | ( | 3 )
| Filter by ZipCode |  |  | 10%
30%
2016-12-29
View Collaborative details |  | 2016-12-29 | White |  | 0% | 100%
| Select Items |  |  | 0% |  |  | View Collaborative details
| Select Quantities |  |  | 0% |  |  | ( | 6 )
| Look up prices |  |  | 0%
| Calculate total |  |  | 0%
| Add taxes |  |  | 0% |  |  | 0%
| Calculate Grand Total |  |  | 0%
2016-12-29
Search by Collaborative details |  | 2016-12-19 | White |  | 0% | 100%
| Get Name |  |  | 0% |  |  | Search by Collaborative details
| Get Address |  |  | 0% |  |  | ( | 7 )
| Get Phone numbers |  |  | 0%
| Check if present |  |  | 0%
| Save if new |  |  | 0%
| Update if existing |  |  | 0% |  |  | 0%
| Confirm save |  |  | 0%
2016-12-19
Collaborative Details forms |  | 2016-12-08 | White |  | 0% | 100%
| Set order ID |  |  | 0% |  |  | Collaborative Details forms
| Get order items |  |  | 0% |  |  | ( | 5 )
| Calculate total |  |  | 0%
| Add taxes |  |  | 0%
| Calculate Grand Total |  |  | 0% |  |  | 0%
2016-12-08
(Blue because in progress yet not due for >14 days)
(Red because overdue)
(Yellow because due within 14 days)
(White because not started yet)
Formulas:
Col. Status = IF(F6=0,"White",IF([Due Date]>TODAY()+14,"Blue",IF([Due Date]>TODAY(),"Yellow","Red")))